## Sheet1
Task | Start | Duration
Notification of grant award | 2016-05-15
Identify additional stakeholders or interested parties to discuss feature attribute needs | May - June
Write a detailed RFP/RFQ to select best contractor to complete project | June
Advertise RFP/RFQ | July | +/- 30 days
Select contractor | TBD | 2 weeks
Meet with contractor and finalize contract needs and requirements | TBD
Contractor begins work as outlined by grant and RFP/RFQ | late August | until completed or funds are final
Monthly QA/QC of project work from contractor | TBD
Interim Project report | TBD
Final Project report | September, 2017

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only